## Inverter
Requirements | Module | Source File | Functions | Description | Status | Module Test | Integration Test | System Test | Comments
| ADC | mdlADC.c | mdlADC_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlADC_startConversion |  | Complete | Successful | Successful | Not Tested
|  |  | mdlADC_readResult |  | Complete | Successful | Successful | Not Tested
|  |  | mdlADC_initADC |  | Complete | Successful | Successful | Not Tested
|  |  | mdlADC_initSOC |  | Complete | Successful | Successful | Not Tested
|  |  | mdlADC_get_Temp_uC |  | See Comment | Successful | Successful | Not Tested | Needs to be moved to measurement module
| CAN | mdlCAN.c | mdlCAN_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_exec |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_transmitMessage |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_dataWait |  | See Comment | Successful | Not Tested | Not Tested | check if used
|  |  | mdlCAN_setupModules |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_startModules |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_setupMessages |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_calculateSleeptime |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_transmit_receive |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_getDataRef |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_dataUpdated |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_updateData |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCAN_readMessage |  | Complete | Successful | Successful | Not Tested
| CMPSS | mdlCMPSS.c | mdlCMPSS_init |  | Complete | Successful | Successful | Not Tested | Need to add additional functionality here to check
|  |  | mdlCMPSS_deinit_development |  | Complete | Successful | Successful | Not Tested | comparator bit set and not just latch. To change the
|  |  | mdlCMPSS_isCompLatched |  | Complete | Successful | Successful | Not Tested | logic of the state machine
|  |  | mdlCMPSS_clearCompLatch |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCMPSS_setMaxRampValue |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCMPSS_DACinitValue |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCMPSS_DACvalueUpdate |  | Complete | Successful | Successful | Not Tested
|  |  | mdlCMPSS_initCMPMux |  | See Comment | Successful | Successful | Not Tested | Add description
| Debounce | mdlDebounce.c | mdlDebounce_init |  | Complete | Successful | Successful | Not Tested | Add details and documentation in the module
|  |  | mdlDebounce_getState |  | Complete | Successful | Successful | Not Tested
|  |  | mdlDebounce_update |  | Complete | Successful | Successful | Not Tested
| EPWM | mdlEPWM.c | mdlEPWM_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlEPWM_initEventTriggers |  | Complete | Successful | Successful | Not Tested
|  |  | mdlEPWM_initTripZones |  | Complete | Successful | Successful | Not Tested
|  |  | mdlEPWM_initDigitalCompare |  | Complete | Successful | Successful | Not Tested
|  |  | mdlEPWM_initDeadband |  | Complete | Successful | Successful | Not Tested
|  |  | mdlEPWM_forceTripZone |  | Complete | Successful | Successful | Not Tested
|  |  | mdlEPWM_isTripZoneFlagged |  | Complete | Successful | Successful | Not Tested
|  |  | mdlEPWM_clearTripZoneFlags |  | Complete | Successful | Successful | Not Tested
| Error | mdlError.c | mdlError_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlError_get |  | Complete | Successful | Successful | Not Tested
|  |  | mdlError_getErrorCode |  | Complete | Successful | Successful | Not Tested
|  |  | mdlError_isEnabled |  | Complete | Successful | Successful | Not Tested
|  |  | mdlError_set |  | Complete | Successful | Successful | Not Tested
|  |  | mdlError_clear |  | Complete | Successful | Successful | Not Tested
| FIFO | mdlFIFO.c | mdlFIFO_init |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_write |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_read |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_used |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_free |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_reset |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_getCounter |  | See Comment | See Comment | See Comment | See Comment | Only for DEBUG
| HAL | mdlHAL.c | mdlHAL_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlHAL_getPinNumber |  | Complete | Successful | Successful | Not Tested
|  |  | mdlHAL_readPin |  | Complete | Successful | Successful | Not Tested | Check if being used
|  |  | mdlHAL_writePin |  | Complete | Successful | Successful | Not Tested | Check if being used
|  |  | mdlHAL_togglePin |  | Complete | Successful | Successful | Not Tested | Check if being used
| Measurement | mdlMeasurement.c | mdlMeasurement_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlMeasurement_update |  | Complete | Successful | Successful | Not Tested
| Monitor | mdlMonitor.c | mdlMonitor_init |  | See Comment | See Comment | Not Tested | Not Tested | Check with Sebastian - Implemented but not
|  |  | mdlMonitor_exec |  | See Comment | See Comment | Not Tested | Not Tested | active?
|  |  | mdlMonitor_reset |  | See Comment | See Comment | Not Tested | Not Tested
|  |  | mdlMonitor_call |  | See Comment | See Comment | Not Tested | Not Tested
| NTC | mdlNTC.c | float mdlNTC_getTemp |  | Complete | Successful | Not Tested | Not Tested | Figure out if this is being used or not and adjust if needed
| OpsMode | mdlOpsMode.c | mdlOpsMode_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlOpsMode_getMode |  | Complete | Successful | Successful | Not Tested
| SCI | mdlSCI.c | mdlSCI_init |  | Complete | Successful | Successful | Not Tested
| (Serial Comm) |  | mdlSCI_exec |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSCI_writeCharArray |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSCI_transmit |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSCI_receive |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSCI_clearBreakDetect |  | Complete | Successful | Successful | Not Tested
| State Machine | mdlSM.c | mdlSM_init |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_exec |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_getStateID |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_controlFans |  | Complete | See Comment | See Comment | See Comment | Not used
|  |  | mdlSM_updatePeakRef |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_flagError |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_checkForErrors |  | Complete | Successful | Successful | Not Tested | This checks if CMPSS are latched or not. Need to write
|  |  | mdlSM_AddNewFunction |  | Not Implemented | Not Tested | Not Tested | Not Tested
|  |  | mdlSM_clearAllErrors |  | Complete | Successful | Successful | Not Tested | another function to check CMPSS is set or not.
|  |  | mdlSM_Boot |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_Standby |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_Operate |  | Complete | Successful | Successful | Not Tested
|  |  | mdlSM_Error |  | Complete | Successful | Successful | Not Tested | Document changes
|  | mdlJSM.c | isTran |  | See Comment | Successful | Successful | Not Tested | Add extensive documentation to this section. Refactor
|  |  | finishTran |  | See Comment | Successful | Successful | Not Tested
|  |  | JSM_init |  | See Comment | Successful | Successful | Not Tested
|  |  | JSM_exec |  | See Comment | Successful | Successful | Not Tested
| Fullbridge | Fullbridge.c | Fullbridge_init |  | Complete | Successful | Successful | Not Tested
|  |  | Fullbridge_disable |  | Complete | Successful | Successful | Not Tested
|  |  | Fullbridge_enable |  | Complete | Successful | Successful | Not Tested
|  |  | Fullbridge_Ramp_Phase |  | Complete | Successful | Successful | Not Tested
|  |  | Fullbridge_Ramp_Ref |  | Complete | Successful | Successful | Not Tested
|  |  | Fullbridge_Ramp_resetPhase |  | Complete | Successful | Successful | Not Tested
|  |  | Fullbridge_Ramp_resetRef |  | Complete | Successful | Successful | Not Tested
| Main | main.c | initSystickTimer |  | Complete | Successful | Successful | Not Tested | Refactor initialization functions to separate c file
|  |  | initCla1 |  | Complete | Successful | Successful | Not Tested
|  |  | initXBAR |  | Complete | Successful | Successful | Not Tested
|  |  | updateReadings |  | Complete | Successful | Successful | Not Tested
|  |  | update_Status_CANMsgData |  | Complete | Successful | Successful | Not Tested
|  |  | update_Info_CANMsgData |  | Complete | Successful | Successful | Not Tested
|  |  | update_Data_MuxInverter_CANMsgData |  | Complete | Successful | Successful | Not Tested
|  |  | update_Data_MuxGyrator_CANMsgData |  | Complete | Successful | Successful | Not Tested
|  |  | update_Data_MuxVarious_CANMsgData |  | Complete | Successful | Successful | Not Tested
|  |  | read_Control_CANMsgData |  | Complete | Successful | Successful | Not Tested
|  |  | read_DACupdate_CANMsgData |  | Complete | Successful | Successful | Not Tested
|  |  | updateTemperatures |  | Complete | Successful | Successful | Not Tested
|  |  | main |  | Complete | Successful | Successful | Not Tested
C39P3MG8G5MT

## PFC
Requirements | Module | Source File | Functions | Description | Status | Module Test | Integration Test | System Test | Comments
| ADC | mdlADC.c | mdlADC_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_startConversion |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_readResult |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_initADC |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_initSOC |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_get_Temp_uC |  | See Comment | Successful | Not Tested | Not Tested | Needs to be moved to measurement module
| CAN | mdlCAN.c | mdlCAN_init |  | Complete | Successful | Not Tested | Not Tested | CAN communication needs to be updated with
|  |  | mdlCAN_exec |  | Complete | Successful | Not Tested | Not Tested | debug control options
|  |  | mdlCAN_transmitMessage |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_dataWait |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_setupModules |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_startModules |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_setupMessages |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_calculateSleeptime |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_transmit_receive |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_getDataRef |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_dataUpdated |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_updateData |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_readMessage |  | In Progress | Successful | Not Tested | Not Tested
| CMPSS | mdlCMPSS.c | mdlASysCtrl_initCMPMux |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_init |  | In Progress | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_deinit_development |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_isCompLatched |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_clearCompLatch |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_setMaxRampValue |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_DACinitValue |  | Complete | Successful | Not Tested | Not Tested | New, restructure DAC initialization path
|  |  | mdlCMPSS_DACvalueUpdate |  | Not Implemented | Not Tested | Not Tested | Not Tested
|  |  | mdlASysCtrl_initCMPMux |  | Complete | Successful | Not Tested | Not Tested
| Debounce | mdlDebounce.c | mdlDebounce_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlDebounce_getState |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlDebounce_update |  | Complete | Successful | Not Tested | Not Tested
| EPWM | mdlEPWM.c | mdlEPWM_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initEventTriggers |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initTripZones |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initDigitalCompare |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initDeadband |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_forceTripZone |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_isTripZoneFlagged |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_clearTripZoneFlags |  | Complete | Successful | Not Tested | Not Tested
| Error | mdlError.c | mdlError_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_get |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_getErrorCode |  | Complete | Successful | Not Tested | Not Tested | Add statement to clear error flag
|  |  | mdlError_isEnabled |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_set |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_clear |  | Complete | Successful | Not Tested | Not Tested
| FIFO | mdlFIFO.c | mdlFIFO_init |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_write |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_read |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_used |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_free |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_reset |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_getCounter |  | See Comment | See Comment | See Comment | See Comment | Only for DEBUG
| HAL | mdlHAL.c | mdlHAL_init |  | In Progress | Successful | Errors | Not Tested | 2 pins were configured incorrectly
|  |  | mdlHAL_getPinNumber |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlHAL_readPin |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlHAL_writePin |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlHAL_togglePin |  | Complete | Successful | Not Tested | Not Tested
| Measurement | mdlMeasurement.c | mdlMeasurement_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlMeasurement_update |  | Complete | Successful | Not Tested | Not Tested
| Monitor | mdlMonitor.c | mdlMonitor_init |  | In Progress | Errors | Not Tested | Not Tested | Check with Sebastian - Implemented but not
|  |  | mdlMonitor_exec |  | Complete | See Comment | Not Tested | Not Tested | active?
|  |  | mdlMonitor_reset |  | Complete | See Comment | Not Tested | Not Tested
|  |  | mdlMonitor_call |  | Complete | See Comment | Not Tested | Not Tested
| NTC | mdlNTC.c | float mdlNTC_getTemp |  | Complete | Successful | Not Tested | Not Tested
| OpsMode | mdlOpsMode.c | mdlOpsMode_init |  | Complete | Successful | Not Tested | Not Tested | Incorrect comments, typedef, etc.
|  |  | mdlOpsMode_getMode |  | Complete | Successful | Not Tested | Not Tested | Corrected and updated documentation
| SCI | mdlSCI.c | mdlSCI_init |  | Complete | Successful | Not Tested | Not Tested
| (Serial Comm) |  | mdlSCI_exec |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_writeCharArray |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_transmit |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_receive |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_clearBreakDetect |  | Complete | Successful | Not Tested | Not Tested

## Common
Requirements | Module | Source File | Functions | Description | Status | Module Test | Integration Test | System Test | Comments
| ADC | mdlADC.c | mdlADC_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_startConversion |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_readResult |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_initADC |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_initSOC |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlADC_get_Temp_uC |  | See Comment | Successful | Not Tested | Not Tested | Needs to be moved to measurement module
| CAN | mdlCAN.c | mdlCAN_init |  | Complete | Successful | Not Tested | Not Tested | CAN communication needs to be updated with
|  |  | mdlCAN_exec |  | Complete | Successful | Not Tested | Not Tested | debug control options
|  |  | mdlCAN_transmitMessage |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_dataWait |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_setupModules |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_startModules |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_setupMessages |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_calculateSleeptime |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_transmit_receive |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_getDataRef |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_dataUpdated |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_updateData |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCAN_readMessage |  | In Progress | Successful | Not Tested | Not Tested
| CMPSS | mdlCMPSS.c | mdlASysCtrl_initCMPMux |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_init |  | In Progress | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_deinit_development |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_isCompLatched |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_clearCompLatch |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_setMaxRampValue |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlCMPSS_DACinitValue |  | Complete | Successful | Not Tested | Not Tested | New, restructure DAC initialization path
|  |  | mdlCMPSS_DACvalueUpdate |  | Complete | Not Tested | Not Tested | Not Tested
|  |  | mdlASysCtrl_initCMPMux |  | Complete | Successful | Not Tested | Not Tested
| Debounce | mdlDebounce.c | mdlDebounce_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlDebounce_getState |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlDebounce_update |  | Complete | Successful | Not Tested | Not Tested
| EPWM | mdlEPWM.c | mdlEPWM_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initEventTriggers |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initTripZones |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initDigitalCompare |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_initDeadband |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_forceTripZone |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_isTripZoneFlagged |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlEPWM_clearTripZoneFlags |  | Complete | Successful | Not Tested | Not Tested
| Error | mdlError.c | mdlError_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_get |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_getErrorCode |  | Complete | Successful | Not Tested | Not Tested | Add statement to clear error flag
|  |  | mdlError_isEnabled |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_set |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlError_clear |  | Complete | Successful | Not Tested | Not Tested
| FIFO | mdlFIFO.c | mdlFIFO_init |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_write |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_read |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_used |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_free |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_reset |  | See Comment | See Comment | See Comment | See Comment
|  |  | mdlFIFO_getCounter |  | See Comment | See Comment | See Comment | See Comment | Only for DEBUG
| Measurement | mdlMeasurement.c | mdlMeasurement_init |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlMeasurement_update |  | Complete | Successful | Not Tested | Not Tested
| Monitor | mdlMonitor.c | mdlMonitor_init |  | In Progress | Errors | Not Tested | Not Tested | Check with Sebastian - Implemented but not
|  |  | mdlMonitor_exec |  | Complete | See Comment | Not Tested | Not Tested | active?
|  |  | mdlMonitor_reset |  | Complete | See Comment | Not Tested | Not Tested
|  |  | mdlMonitor_call |  | Complete | See Comment | Not Tested | Not Tested
| NTC | mdlNTC.c | float mdlNTC_getTemp |  | Complete | Successful | Not Tested | Not Tested
| OpsMode | mdlOpsMode.c | mdlOpsMode_init |  | Complete | Successful | Not Tested | Not Tested | Incorrect comments, typedef, etc.
|  |  | mdlOpsMode_getMode |  | Complete | Successful | Not Tested | Not Tested | Corrected and updated documentation
| SCI | mdlSCI.c | mdlSCI_init |  | Complete | Successful | Not Tested | Not Tested
| (Serial Comm) |  | mdlSCI_exec |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_writeCharArray |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_transmit |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_receive |  | Complete | Successful | Not Tested | Not Tested
|  |  | mdlSCI_clearBreakDetect |  | Complete | Successful | Not Tested | Not Tested

## DataValidation
Status Options | Test Options
Not Implemented | Successful
In Progress | Not Tested
Complete | See Comment
See Comment | Errors